## How to choose
INSIGHTS SPOTTER · RAID LOG TEMPLATE
Two expansions are equally valid. Pick one primary set of four letters per register. Blank cells mean not supplied — do not invent values.
This workbook never assumes a single industry meaning of RAID. Write your chosen expansion in the Project setup sheet before sharing.
Expansion | Letters | Use when
Assumptions & Dependencies | Risks · Assumptions · Issues · Dependencies | Unvalidated beliefs or external wait-states drive delivery risk; actions/decisions already live elsewhere.
Actions & Decisions | Risks · Actions · Issues · Decisions | Weekly triage centres on owners of work and authorised choices.
Shared letters
Risk and Issue appear in both expansions. Cover them once, then add either Assumption+Dependency or Action+Decision.
ID prefixes (avoid A/D collisions)
RSK | Risk
ASM | Assumption
ISS | Issue
DEP | Dependency
ACT | Action
DEC | Decision
Sheets in this workbook
Project setup · Letter guide · RAID register (all six types available; filter to your four) · Worked example. Status lists match practical starting sets; adapt to your governance.
Insights Spotter · Free template · No warranty that this matches any specific method product. Adapt fields to your organisation.

## Project setup
PROJECT SETUP
Complete this before sharing the register. Choosing an expansion is a project decision, not a formatting preference.
If you later change expansion, re-prefix IDs and archive the old sheet rather than silently renaming types.
Field | Value | Notes
Project name |  | Required
Chosen RAID expansion |  | Pick from list: Assumptions & Dependencies OR Actions & Decisions
Register owner |  | Usually the project manager
Review rhythm | Weekly | Plus urgent triggers between meetings
Escalation forum |  | e.g. SteerCo / sponsor
Date format | YYYY-MM-DD | Keep ISO dates
Status customisation note | None | Record if you change the starting status sets

## Letter guide
LETTER GUIDE · EVERY RAID LETTER
Definition, owner rule, status set, escalation trigger and a fictional example for each letter. Use with either expansion.
Examples are teaching shapes only. Do not treat them as benchmarks or statistics.
Letter | Expansion | Definition | Owner rule | Status set (starting) | Escalate when | Example (fictional)
Risk | Both | Uncertain event/condition that could affect objectives if it occurs. | One named person who maintains the record and drives the response. | Open; Monitoring; Mitigated; Accepted; Closed | Readiness cannot be evidenced by review date, or impact needs sponsor authority. | RSK-001 — Test environment may be unavailable by 6 Nov 2026; integration testing may miss readiness review.
Issue | Both | Current problem that already affects delivery or will without prompt resolution. | One named person accountable for resolution and current next step. | Open; In progress; Resolved; Accepted; Closed | Retest fails or fix threatens the next milestone. | ISS-001 — Booking confirmation interface failed integration test on 2 Nov 2026.
Assumption | Assumptions & Dependencies | Belief treated as true for planning that is not fully validated; plan would change if false. | Person who owns validation evidence. | Proposed; Validated; Invalidated; Retired | Validation overdue or evidence contradicts the belief. | ASM-001 — Staff users complete booking without training by trial start; validate by usability check 4 Nov.
Dependency | Assumptions & Dependencies | Work, information, access or decision needed from another party before a committed step can finish. | Internal chase owner; name external contact where possible. | Open; Monitoring; Satisfied; Blocked; Closed | Needed item will miss required-by date or provider is unresponsive. | DEP-001 — Platform Ops credentials required by 6 Nov for integration testing.
Action | Actions & Decisions | Agreed task with named owner, due date and clear completion condition. | Person who will complete the work or obtain completion evidence. | Open; In progress; Closed; Superseded | Due date will be missed or repeated slips lack a changed response. | ACT-001 — Leo confirms fallback environment supports required interfaces by 4 Nov 2026.
Decision | Actions & Decisions | Agreed choice with rationale, authority and consequences. A proposal is not an approval. | Record owner distinct from approving authority/forum where required. | Proposed; Approved; Partially approved; Rejected; Superseded | A blocking choice has no authorised forum scheduled, or an approval is ignored in implementation. | DEC-001 — Sponsor approved staff-only trial on 3 Nov 2026 pending interface fix.

## RAID register
RAID REGISTER
Filter Type to your four letters. Use RSK/ASM/ISS/DEP or RSK/ACT/ISS/DEC prefixes. One owner per row. Close only with evidence.
AI USE: Ask an assistant to flag missing owner, date, status or evidence against this sheet; review every suggestion before changing the live log.
Open / active rows |  | Overdue reviews (date < today & not terminal) | (Filter Review date manually each week — Excel tables optional)
ID | Type | Summary | Details | Owner | Status | Response / next step | Likelihood | Impact | Priority | Review or due date | Escalation condition | Evidence / source reference | Related IDs | Last updated

## Worked example
WORKED EXAMPLE · FICTIONAL TRIAL
Illustrative booking-service trial. Shows both expansions’ letter types with connected rows. Not a live register.
READ THIS FIRST: Dates and names are fictional. Use as a shape for good rows, not as copied content for a real project.
ID | Type | Summary | Details | Owner | Status | Response / next step | Likelihood | Impact | Priority | Review or due date | Escalation condition | Evidence / source reference | Related IDs | Last updated
RSK-001 | Risk | Test environment may be unavailable by 6 Nov 2026 | Integration testing may miss trial readiness review. | Maya | Monitoring | Confirm readiness; assess fallback route. | High | High |  | 2026-11-03 | Escalate to sponsor if readiness not evidenced at review. | Readiness note, environment assessment, 2 Nov 2026 | ACT-001 | 2026-11-02
ACT-001 | Action | Verify fallback environment supports required interfaces | Establish whether fallback testing is viable. | Leo | Open | Complete compatibility testing; seek technical lead review. |  | Medium |  | 2026-11-04 | Escalate to PM if review cannot finish by due date. | Readiness meeting note, 2 Nov 2026 | RSK-001 | 2026-11-02
ISS-001 | Issue | Booking confirmation interface failed integration test | Prevents end-to-end readiness check. | Noor | In progress | Fix and retest planned for 5 Nov. |  | High | High | 2026-11-05 | Escalate if retest fails or fix threatens readiness. | Test report, 2 Nov 2026 | DEC-001 | 2026-11-02
DEC-001 | Decision | Limit trial to staff users | Unresolved interface issue makes wider trial premature. | Eva | Approved | Track invitation update as separate action. |  | High |  | 2026-11-03 | Refer external-user requests to sponsor. | Readiness meeting note, sponsor approval, 3 Nov 2026 | ISS-001 | 2026-11-03
ASM-001 | Assumption | Staff users complete booking without training materials by trial start | If false, trial needs a training pack decision. | Priya | Proposed | Run usability check; record pass/fail evidence. |  | Medium |  | 2026-11-04 | Escalate if invalidated before trial start. | Usability check plan, 1 Nov 2026 | DEC-001 | 2026-11-01
DEP-001 | Dependency | Test environment credentials from Platform Ops by 6 Nov | Required for integration testing window. | Maya | Open | Chase Platform Ops; confirm access usable. |  | High |  | 2026-11-03 | Escalate to sponsor if access not confirmed at review. | Access request ticket, 28 Oct 2026 | RSK-001 | 2026-10-28