# Weekly project status report

A short, evidence-aware update for the people who need to act or decide.

FICTIONAL SCENARIO  ·  All names, dates and figures below are illustrative.

| PROJECT Service request rollout | REPORTING PERIOD 12–16 Oct 2026 | PREPARED BY Project manager | INFORMATION CHECKED 16 Oct 2026 |
| --- | --- | --- | --- |

| AMBER | Pilot is useful, but four users still need a follow-up before the next rollout decision. |
| --- | --- |

| Progress and next milestone Completed this period Two pilot teams tested the new intake; 18 of 22 test requests were completed. The remaining four need follow-up. Next milestone Next period Complete the four follow-ups and confirm whether the outstanding issues change the rollout recommendation. | Attention and decisions Issue or risk Four pilot users have not completed a request. If their issue is a process barrier, a wider rollout could reproduce it. Owner: J. Patel · follow up by 21 Oct 2026 · source: pilot log. Decision or support needed Choose phased rollout or one release date by 22 Oct 2026. Decision maker: sponsor. Waiting leaves the deployment approach unconfirmed. Related decision: D-002. Record references A-004 · D-002. See the linked action and decision logs for full context. |
| --- | --- |

| Milestone | Agreed date | Forecast | Owner |
| --- | --- | --- | --- |
| Pilot review | 30 Oct 2026 | 06 Nov 2026 | R. Chen |

READING NOTE  Blank = not supplied or confirmed. “Not assessed” is not a healthy status. Keep fact, forecast and recommendation distinct; verify the source before sending.